## Design Reviews
Design Review Template
Review ID / Title | Date / Participants | Initiative / Epic Reference | Design Topics | Summary of Discussion | Decisions Taken | Open Questions / Risks | Actions / Owners | Next Review / Checkpoint
DR-001: API Gateway Integration | 2025-10-12 / EA Team, Dev Team, Security Lead | CRM Integration Epic #142 | Authentication flow, token caching, logging | Validated JWT flow; rate limiting required on gateway. | Proceed with gateway-based rate limiting. | Impact on API performance to be tested. | DevOps Team to perform load test. | Sprint 24 review (in 2 weeks)
DR-002: Data Platform Onboarding | 2025-09-30 / Data Arch, BI Team, Infra Lead | Analytics Platform Phase 2 | Data ingestion, metadata governance | Aligned on metadata tagging; need clearer ownership model. | Use existing data catalog for all ingestion jobs. | Data ownership matrix not finalized. | Data Governance team to define owners. | Next governance sync (2025-10-20)
DR-003: Identity Modernization | 2025-09-18 / Security Arch, PO, Infra Team | SSO Migration Project | Token management, backward compatibility | Confirmed Azure AD integration; agreed to phased rollout. | Implement hybrid auth for transition period. | Legacy apps still lack SSO readiness. | Application owners to adapt before go-live. | Next review Q4 planning session
Note: Design reviews are short, structured discussions — focus on understanding and alignment, not formal approval.