## Decision Logs
Architecture Decision Log Template
Decision ID / Title | What was decided? | Why was it decided? | When was it decided? | Who was involved? | Options Considered | Implications / Consequences | Status (Confirmed/Under Review/Deprecated) | Next Review / Checkpoint
DEC-001: Adopt Azure AD | All new applications will use Azure AD for authentication. | To consolidate identity management and strengthen security. | 2025-10-12 | EA Board, Security Team, IT Ops | Keycloak, Okta, Azure AD | Migration required for legacy apps; update SSO policies. | Confirmed | Reevaluate after full rollout (Q3 2026)
DEC-002: Use Kafka for async integration | Adopt Kafka as the standard for event-based communication. | Improves scalability, resilience, and decoupling between systems. | 2025-08-05 | Integration Team, Solution Architects | RabbitMQ, Kafka, Azure Service Bus | Requires schema governance and monitoring setup. | Confirmed | Review after 6 months of production use
DEC-003: Decommission custom reporting tool | Replace legacy reporting system with Power BI platform. | Aligns with enterprise analytics strategy and reduces maintenance costs. | 2025-07-20 | Data Governance, BI Team | QlikView, Power BI, Tableau | Migration of reports; retraining needed for analysts. | Deprecated | N/A
Note: Each decision log should be concise, factual, and revisited periodically to ensure ongoing relevance.